## 28.03.2024
Simply Rugby ¦ Graded Unit Checklist
Page name | Type | Progress | Tweaks Needed
article.php | Class | Finished
basket.php | Class | Finished
components.php | Class | Finished
connection.php | Class | Finished
order.php | Class | Finished
pet.php | Class | Finished
sql.php | Class | Almost Finished | Give "test" functions more specific names
user.php | Class | Finished
utils.php | Class | Finished
article-card.php | Component | Finished
basket-empty.php | Component | Finished
basket-footer.php | Component | Finished
basket-header.php | Component | Finished
basket-row.php | Component | Finished
book-card.php | Component | Finished
book-single.php | Component | Finished
footer.php | Component | Finished
form-validation.php | Component | Finished
header-alt.php | Component | Finished
header.php | Component | Finished
no-books-found.php | Component | Finished
no-orders-found.php | Component | Finished
no-single-book-found.php | Component | Finished
order-head.php | Component | Finished
order-row.php | Component | Finished
register-validation.php | Component | Finished
about.php | Web Page | Finished
add-pet.php | Web Page | Almost Finished | Change field names to correct names
articles.php | Web Page | Finished
basket.php | Web Page | Finished
book.php | Web Page | Finished
booking.php | Web Page | Finished
calendar.php | Web Page | Finished
Checklist.xlsx | Web Page | Finished
checkout.php | Web Page | Finished
contact.php | Web Page | Finished
database.sql | Web Page | Finished
index.php | Web Page | Finished
login.php | Web Page | Finished
logout.php | Web Page | Finished
pet-list.php | Web Page | Finished
pet.php | Web Page | Finished
register.php | Web Page | Finished
success.php | Web Page | Finished
user.php | Web Page | Finished
Activity Name |  | Progress | Tweaks Needed
Code Commentary |  | Not started
Document Name | Testing Type | Progress | Tweaks Needed
Functionality testing spreadsheet | Functionality testing | Almost Finished | Update the document with latest tests
User acceptance testing form | UAT | Not started
Usability testing form | Usability testing | Not started
Compability testing spreadsheet | Compability testing | Not started
Mobile Testing | Mobile Testing | Not started

## 29.03.2024
Simply Rugby ¦ Graded Unit Checklist
Page name | Type | Progress | Tweaks Needed
article.php | Class | Finished
basket.php | Class | Finished
components.php | Class | Finished
connection.php | Class | Finished
order.php | Class | Finished
pet.php | Class | Finished
sql.php | Class | Finished
user.php | Class | Finished
utils.php | Class | Finished
article-card.php | Component | Finished
basket-empty.php | Component | Finished
basket-footer.php | Component | Finished
basket-header.php | Component | Finished
basket-row.php | Component | Finished
book-card.php | Component | Finished
book-single.php | Component | Finished
footer.php | Component | Finished
form-validation.php | Component | Finished
header-alt.php | Component | Finished
header.php | Component | Finished
no-books-found.php | Component | Finished
no-orders-found.php | Component | Finished
no-single-book-found.php | Component | Finished
order-head.php | Component | Finished
order-row.php | Component | Finished
register-validation.php | Component | Finished
about.php | Web Page | Finished
add-pet.php | Web Page | Finished
articles.php | Web Page | Finished
basket.php | Web Page | Finished
book.php | Web Page | Finished
booking.php | Web Page | Finished
calendar.php | Web Page | Finished
Checklist.xlsx | Web Page | Finished
checkout.php | Web Page | Finished
contact.php | Web Page | Finished
database.sql | Web Page | Finished
index.php | Web Page | Finished
login.php | Web Page | Finished
logout.php | Web Page | Finished
pet-list.php | Web Page | Finished
pet.php | Web Page | Finished
register.php | Web Page | Finished
success.php | Web Page | Finished
user.php | Web Page | Finished
Activity Name |  | Progress | Tweaks Needed
Code Commentary |  | Not started
Document Name | Testing Type | Progress | Tweaks Needed
Functionality testing spreadsheet | Functionality testing | Finished
Usability testing form | Usability testing | Collect Responses
Compability testing spreadsheet | Compability testing | Not started
Mobile Testing | Mobile Testing | Not started